## 📋 Master Overview
ANOTE AI RESEARCH FELLOWSHIP 2026 — Research Tracker
Summer 2026 ¦ T1a-T5 (Active) + T6-T23 (Backlog) ¦ 25 Total Paper Ideas ¦ Last Updated: 2026-03-27
Track # | Track Name | Research Question (1-sentence) | Intern Lead | Paper Lead | Next Deadline | Next Venue | Overall Status | GitHub Repo | Research Design Doc | Claude Code Prompt | Notes
T1a | AgenticEval: Agentic Tool-Calling Evaluation & Intent Alignment | Does BFCL rank predict enterprise trustworthiness, and how do SLMs compare on intent alignment vs. syntactic accuracy? | T1 sub-team A (eval focus) | Spurthi Setty | Aug 1, 2026 | AAAI 2027 / NeurIPS 2026 ED | In Progress | [GitHub URL] | [Research Design URL] | [Claude Code Prompt URL] | EnterpriseBench (200 tasks, 4 verticals). 5 SLM families × 4 prompting conditions. Evaluation paper. Data built by T1b.
T1b | EnterpriseSynth: Synthetic Data Generation for Private Agentic Workflows | Given only a proprietary API schema, can we generate verified SFT + eval data without executing a single real API call? | T1 sub-team B (engineering focus) [sub-team split TBD] | Spurthi Setty | Aug 1, 2026 | AAAI 2027 / NeurIPS 2026 ED | Not Started | [GitHub URL] | [Research Design URL] | [Claude Code Prompt URL] | Framework paper. 3 generation strategies. Mock execution simulator. Builds EnterpriseBench used by T1a. Start Week 1.
T2a | AnnotateBench: Benchmarking Annotation Requirements Across NLP Tasks | How much labeled data do different annotation strategies need across NLP task types, and what do the learning curves look like? | Sub-team A (2–3 interns) | [TBD] | Aug 1, 2026 | AAAI 2027 / NeurIPS 2026 ED | Not Started | [GitHub URL] | [Research Design URL] | [Claude Code Prompt URL] | 5 strategies × 10 datasets × 5 budgets. Shared codebase with T2b.
T2b | AnnotateROI: Enterprise Framework for Measuring Annotation Return on Investment | How should enterprises measure annotation ROI and determine when they have labeled enough data? | Sub-team B (2–3 interns) | [TBD] | Aug 1, 2026 | AAAI 2027 | Not Started | [GitHub URL] | [Research Design URL] | [Claude Code Prompt URL] | Builds on T2a results. Adds cost model, stopping criterion, LLM-vs-human decision tree.
T3 | Human-AI Teaming for Preference Data & Red-Teaming | How does the human-AI collaboration protocol for preference dataset construction affect downstream model behavior and bias? | [Intern TBD] | [TBD] | Aug 1, 2026 | AAAI 2027 | Not Started | [GitHub URL] | [Research Design URL] | [Claude Code Prompt URL] | MS-level preferred. 3-condition experimental design. High ceiling.
T4 | Failure Propagation in Agentic RAG Pipelines | How do retrieval errors propagate through multi-step agentic pipelines — compound, corrected, or isolated? | [Intern TBD] | Spurthi Setty | Aug 1, 2026 | AAAI 2027 / Expert Systems | Not Started | [GitHub URL] | [Research Design URL] | [Claude Code Prompt URL] | Extends arXiv:2404.07221 + SIGIR submission. Clearest journal path.
T5 | RetrievalBench: Cross-Domain Retrieval Technique Benchmark for Long Structured Documents | Which combination of retrieval techniques produces the best results for structured documents, and does the winner generalize across domains? | [1–2 interns] | Spurthi Setty | Aug 1, 2026 (AAAI) / Jan 2027 (SIGIR) | SIGIR 2027 / AAAI 2027 / NeurIPS ED | Not Started | [GitHub URL] | [Research Design URL] | [Claude Code Prompt URL] | Extends arXiv:2404.07221 (80+ citations). Financial domain DONE. 3 new domains: legal (CUAD), medical (PubMedQA), technical (TechQA). 6-level ablation × 4 domains = 24 conditions.
T-Theory | Sample Complexity Theory for Active Learning — DEPRIORITIZED | Can we derive tractable sample complexity bounds for active learning in the deep learning regime beyond NTK approximations? | Only if theory-capable intern available | [TBD] | TBD | COLT / NeurIPS Theory | Deprioritized | [GitHub URL] | [Research Design URL] | [Claude Code Prompt URL] | Activate only with top MS/PhD-track intern with PAC learning background. Hanneke 2025 is the hook.
--- New Research Ideas (Added 2026-03-27) ---
T6 | FineTuneBench: Fine-Tuning vs. RAG for Domain Adaptation | Under what conditions does supervised fine-tuning outperform RAG for domain-specific QA, and can we predict this from data characteristics? | [Intern TBD] | Spurthi Setty | Aug 1, 2026 | AAAI 2027 | Not Started | [GitHub URL] | [Design Doc URL] | [Claude Code Prompt URL] | 5 domains x 4 data sizes x 3 adaptation methods. Extends arXiv:2404.07221.
T7 | MultiHopRAG: Multi-Hop Question Answering with Agentic Retrieval Chains | Can agentic decomposition of multi-hop questions improve retrieval accuracy over standard RAG on enterprise documents? | [Intern TBD] | Spurthi Setty | Aug 1, 2026 | AAAI 2027 / SIGIR 2027 | Not Started | [GitHub URL] | [Design Doc URL] | [Claude Code Prompt URL] | Extends T5. MuSiQue, HotpotQA, enterprise multi-hop. 2-4 retrieval steps per question.
T8 | TableRAG: Structured Table Retrieval and Reasoning for Financial QA | How can RAG systems be specialized to retrieve and reason over tabular data in financial documents? | [Intern TBD] | Spurthi Setty | Jan 2027 | SIGIR 2027 | Not Started | [GitHub URL] | [Design Doc URL] | [Claude Code Prompt URL] | Financial tables (income statements, balance sheets). Table-aware chunking + LLM reasoning. FinanceBench tables.
T9 | EmbedBench: Benchmarking Embedding Models for Domain-Specific Retrieval | How do general-purpose vs. domain-specific vs. fine-tuned embedding models compare on retrieval quality across enterprise domains? | [Intern TBD] | [TBD] | Jan 2027 | SIGIR 2027 | Not Started | [GitHub URL] | [Design Doc URL] | [Claude Code Prompt URL] | 8 embedding models x 4 domains x 3 fine-tuning strategies. MTEB-style benchmark. Natural companion to T5.
T10 | LLMClassifyBench: Benchmarking LLMs for Text Classification Across Domain Shifts | How do LLM-based classifiers compare to fine-tuned models under distribution shift, and what is the annotation cost break-even point? | [Intern TBD] | [TBD] | Aug 1, 2026 | AAAI 2027 | Not Started | [GitHub URL] | [Design Doc URL] | [Claude Code Prompt URL] | Extends classification.pdf research. 5 domains x 3 shift types. Directly relevant to Anote product.
T11 | PrivacyRAG: Privacy-Preserving RAG for Sensitive Enterprise Documents | Can we build a RAG system that retrieves relevant context without exposing sensitive entities to the LLM generator? | [Intern TBD] | [TBD] | Jan 2027 | ACL 2027 / EMNLP 2027 | Not Started | [GitHub URL] | [Design Doc URL] | [Claude Code Prompt URL] | PII detection + redaction before LLM. Differential privacy for embeddings. Legal + medical domain.
T12 | AgentMemory: Persistent Memory Architectures for Long-Horizon Agentic Tasks | How do different memory architectures (episodic, semantic, procedural) affect agent performance on long-horizon enterprise tasks? | [Intern TBD] | [TBD] | Aug 1, 2026 | AAAI 2027 | Not Started | [GitHub URL] | [Design Doc URL] | [Claude Code Prompt URL] | Linked to T1a. Tasks spanning >10 tool calls. MemGPT comparison. Memory retrieval efficiency.
T13 | SLMFineTune: Efficient Fine-Tuning Strategies for Small Language Models on Enterprise Data | How do LoRA, QLoRA, prefix tuning, and full fine-tuning compare on enterprise domain tasks with limited labeled data? | [Intern TBD] | [TBD] | Aug 1, 2026 | AAAI 2027 | Not Started | [GitHub URL] | [Design Doc URL] | [Claude Code Prompt URL] | 4 PEFT methods x 3 SLM families x 5 budget levels. Linked to T2a. Practical paper for enterprise ML teams.
T14 | NERBench: Named Entity Recognition Under Domain Shift and Low-Resource Conditions | How much domain-specific annotation is needed for NER to reach clinical/legal/financial expert performance? | [Intern TBD] | [TBD] | Jan 2027 | ACL 2027 / NAACL 2027 | Not Started | [GitHub URL] | [Design Doc URL] | [Claude Code Prompt URL] | 3 specialized NER domains x 5 budget levels x 4 adaptation strategies. Complement to T2a NER slice.
T15 | ChunkingTheory: Automated Optimal Chunking Strategy Selection from Document Features | Is there a principled way to select chunking strategy from document structural features, and can it be automated? | [Intern TBD] | Spurthi Setty | Jan 2027 | SIGIR 2027 | Not Started | [GitHub URL] | [Design Doc URL] | [Claude Code Prompt URL] | Extends T5 chunking ablation. Document-feature predictor for chunking. Financial + legal + technical docs.
T16 | AgenticOrchestration: Multi-Agent Orchestration Patterns for Enterprise Workflows | How do different multi-agent orchestration patterns (sequential, parallel, hierarchical) compare on complex enterprise task completion? | [Intern TBD] | [TBD] | Aug 1, 2026 | AAAI 2027 | Not Started | [GitHub URL] | [Design Doc URL] | [Claude Code Prompt URL] | Linked to T1a. AutoGen, LangGraph comparison. Orchestration overhead vs. task complexity tradeoff.
T17 | SyntheticEval: Reliability of Synthetic Evaluation Datasets for LLM Benchmarking | Can synthetic evaluation datasets generated from LLMs reliably rank models without human-annotated ground truth? | [Intern TBD] | [TBD] | Aug 1, 2026 | AAAI 2027 / NeurIPS 2026 ED | Not Started | [GitHub URL] | [Design Doc URL] | [Claude Code Prompt URL] | Meta-evaluation paper. Linked to T1b. Synthetic vs. human benchmark rank correlation. Kendall tau analysis.
T18 | HallucinationRAG: Hallucination Detection and Mitigation in RAG Pipelines | What is the hallucination rate of RAG systems under varying retrieval quality conditions, and which mitigation strategies are most effective? | [Intern TBD] | Spurthi Setty | Jan 2027 | SIGIR 2027 / AAAI 2027 | Not Started | [GitHub URL] | [Design Doc URL] | [Claude Code Prompt URL] | Extends T4. 5 hallucination types x 4 mitigation strategies. FinanceBench + CUAD. RAGAS faithfulness.
T19 | MultiDocRAG: Cross-Document Reasoning for Enterprise Document Collections | How can RAG systems answer questions that require synthesizing information from multiple documents simultaneously? | [Intern TBD] | [TBD] | Jan 2027 | SIGIR 2027 | Not Started | [GitHub URL] | [Design Doc URL] | [Claude Code Prompt URL] | Multi-doc reasoning. FinanceBench multi-company questions. Knowledge graph + RAG hybrid.
T20 | PromptStability: Measuring and Improving Prompt Robustness in LLM-Based Classifiers | How sensitive are LLM-based text classifiers to prompt variations, and can we design prompts that are robust to paraphrase? | [Intern TBD] | [TBD] | Aug 1, 2026 | AAAI 2027 | Not Started | [GitHub URL] | [Design Doc URL] | [Claude Code Prompt URL] | 50 prompt variants x 5 classification tasks. Robustness metric. Ensemble prompt approach.
T21 | ActiveRAG: Active Learning for RAG Knowledge Base Curation | Can active learning principles guide which documents to add to a RAG knowledge base for maximum QA improvement per document added? | [Intern TBD] | [TBD] | Jan 2027 | SIGIR 2027 | Not Started | [GitHub URL] | [Design Doc URL] | [Claude Code Prompt URL] | Novel intersection of active learning + RAG. Document value scoring. Linked to T2a and T5.
T22 | LLMDataAug: LLM-Based Data Augmentation for Low-Resource NLP Tasks | How effectively can LLMs augment small labeled datasets through paraphrase, back-translation, and counterfactual generation? | [Intern TBD] | [TBD] | Aug 1, 2026 | AAAI 2027 | Not Started | [GitHub URL] | [Design Doc URL] | [Claude Code Prompt URL] | 4 augmentation strategies x 5 NLP tasks x 3 budget levels. Linked to T2a. When does augmentation help vs. hurt?
T23 | OntologyRAG: Ontology-Enhanced Retrieval for Structured Knowledge Domains | Can domain ontologies improve RAG retrieval precision for knowledge-intensive tasks in medicine and law? | [Intern TBD] | [TBD] | Jan 2027 | NAACL 2027 / ACL 2027 | Not Started | [GitHub URL] | [Design Doc URL] | [Claude Code Prompt URL] | Ontology as metadata filter + query expansion. SNOMED (medical) + legal ontologies. Linked to T5.

## T1a — AgenticEval
T1a: AgenticEval — Agentic Tool-Calling Evaluation & Intent Alignment
Research Question | Does BFCL rank predict enterprise deployment trustworthiness, and how do SLMs compare on intent alignment vs. syntactic accuracy?
Core Contribution | EnterpriseBench benchmark (200 tasks, 4 verticals) + 5-dimensional evaluation framework + empirical study of 5 SLM families
Novel Framing | Intent specification as a first-class evaluation object — separate from syntactic tool-call correctness
Models Evaluated | Qwen 2.5 (7B/14B), Llama 3.x (8B/70B), Phi-4, Gemma 2, Mistral 7B/Mixtral — under 4 prompting conditions each
Intern Lead | [TBD — MS-level preferred for benchmark construction]
Paper Lead | Spurthi Setty
Faculty Advisor | Prof. Yue Ning (Stevens CS — NLP) ¦ Prof. Wendy Hui Wang (Stevens CS — Trustworthy ML)
Research Design Doc | [Paste Google Doc URL here]
Claude Code Prompt | [Paste Google Doc URL here]
LaTeX Template | [Paste Google Doc URL here]
GitHub Repo | [Paste GitHub URL here]
Venue / Conference | Type | Tier | Abstract Deadline | Full Paper Deadline | Conference Date | Template Format | Page Limit | Submission Status | CFP Link | OpenReview Link | Notes | Intern Lead | Last Updated
AAAI 2027 | Full Conference | Tier 1 ★ | Jul 25, 2026 | Aug 1, 2026 | Feb 16–23, 2027 | AAAI 2-col | 7 + refs | Not Started | https://aaai.org/conference/aaai/aaai-27/ | TBD | PRIMARY TARGET. Benchmark + empirical study. Double-blind. Highest priority — build toward this deadline. | [Intern TBD] | [Date]
NeurIPS 2026 Workshops (Agentic AI / LLM Eval / Trustworthy ML) | Workshop | Tier 1 ★ | ~Sep 2026 (TBC) | ~Sep–Oct 2026 (TBC) | Dec 6–12, 2026 | NeurIPS 1-col | 4–8 | Not Started | https://neurips.cc/Conferences/2026 | TBD | Parallel fast-track. Submit 4-page preliminary results paper. Gets work in front of community before AAAI. Deadlines TBC — check Sep 2026. | [Intern TBD] | [Date]
EMNLP 2026 Workshops (Industry Track adjacent) | Workshop | Tier 1 ★ | ~Aug 2026 (TBC) | ~Aug 2026 (TBC) | Oct 24–29, 2026 | ACL 2-col | 4–8 | Not Started | https://2026.emnlp.org | TBD | Industry Track published ToolGuard (closest related paper). Workshop deadlines TBC — check Aug 2026. EMNLP main track ARR deadline (May 25) is before fellowship starts. | [Intern TBD] | [Date]
ICLR 2027 | Full Conference | Tier 1 ★ | ~Oct 2026 (TBC) | ~Oct 2026 (TBC) | ~May 2027 | ICLR 1-col | 9 + refs | Not Started | https://iclr.cc | TBD | Stretch target. Higher bar than AAAI. Datasets & Benchmarks track is ideal fit. Attempt if AAAI results are strong. | [Intern TBD] | [Date]
EUMAS 2026 | Full Conference | Tier 2 | ~Apr 2026 (PASSED) | May 18, 2026 (PASSED) | ~Sep 2026 | Springer LNCS | 15 | Missed — Pre-fellowship | https://eumas2026.org | TBD | Deadline passed before fellowship starts. Flag for EUMAS 2027. | N/A | [Date]
AIST 2026 | Full Conference | Tier 3 | TBD | Jul 16, 2026 | ~Oct 2026 | IEEE 2-col | 8 | Not Started | https://openreview.net/group?id=AIST/2026/Conference | https://openreview.net/group?id=AIST/2026/Conference | Backup option. Lower prestige but well-timed for fellowship output. Use if main targets need more time. | [Intern TBD] | [Date]
Expert Systems with Applications (Elsevier Journal) | Journal | Tier 2 | Rolling | Rolling | ~3–5 months post-submission | Elsevier single-col | No limit | Not Started | https://www.sciencedirect.com/journal/expert-systems-with-applications | N/A | Journal extension path. Submit post-fellowship once full evaluation complete. Fast Elsevier review cycle (~2–3 months). Also ideal for T4 RAG paper. | [Intern TBD] | [Date]
KEY HYPOTHESES TO TEST
H1 | BFCL rank ≠ EnterpriseBench rank. |  |  | The ordering of models on BFCL accuracy is a poor predictor of their Intent Alignment Score (IAS) and Sequential Accuracy (SeqAcc). Almost certainly true based on GF experience.
H2 | Model size predicts syntactic accuracy more than intent alignment. |  |  | Scaling 7B → 14B improves BFCL-style correctness, but the gain on IAS is smaller or inconsistent. Suggests intent alignment requires better fine-tuning data, not just scale.
H3 | Prompting strategy has a larger effect on IAS than on syntactic accuracy. |  |  | CoT and ReAct-style prompting improve intent alignment more than raw tool-call correctness. Suggests IAS is a reasoning property, not a recall property.
EVALUATION METRICS TAXONOMY
Abbrev. | Metric Name | Evaluation Method | Description
SeqAcc | Sequential Accuracy | Fully automatic | Fraction of tool calls made in valid dependency order. Penalizes calling get_job_status before submit_job.
IAS | Intent Alignment Score | LLM-as-judge (GPT-4o) + 50 human-annotated gold examples | Structured 0–4 scoring on: (a) primary goal achieved, (b) out-of-intent actions avoided, (c) ambiguity handled consistently with operator intent.
TE | Tool Efficiency | Fully automatic | Ratio of ground-truth calls to model calls. Score of 1.0 = exactly necessary calls. Penalizes over-calling.
RR | Recovery Rate | Automatic — compared against predefined valid recovery traces | Given injected synthetic tool failures, does the agent recover correctly? Tested on 50-task subset.
SA | Scope Adherence | Fully automatic | Binary per trace: did the model invoke any tool outside its authorized scope (blacklist)? Reported as % traces with zero scope violations.

## T1b — EnterpriseSynth
T1b: EnterpriseSynth — Synthetic Data Generation for Private Agentic Workflows
⟵ T1a uses: EnterpriseSynth generates the 200 tasks that become EnterpriseBench. T1b builds the factory; T1a runs the benchmark the factory produces. Same intern cluster — T1b work starts Week 1, T1a starts Week 3 once first data batch exists.
Research Question | Given only a proprietary API schema (OpenAPI/Swagger spec), can we generate high-quality agentic SFT training data AND evaluation ground truth without executing a single real API call?
Core Contribution | EnterpriseSynth: a framework that accepts any OpenAPI/Swagger spec and produces two verified outputs: (1) SFT traces for fine-tuning and (2) eval records with intent specifications for benchmarking — solving the enterprise cold-start data problem.
Why This Gap Exists | APIGen (NeurIPS 2024 D&B), APIGen-MT (NeurIPS 2025 D&B), and TOUCAN (2025) all require public/executable APIs. Enterprises have proprietary internal schemas with no public training data, no ability to batch-execute live APIs (side effects, auth, cost), and no path to bootstrapping. None of the prior frameworks address schema-only generation.
Key Differentiator from Prior Work | Input: schema only (no live execution). Output: dual (SFT + eval). Novel: intent specification generation. Prior work: APIGen/APIGen-MT/TOUCAN generate SFT data only, from public APIs only.
T1a Connection — Structural | EnterpriseSynth IS the methodology behind EnterpriseBench (T1a). T1b generates the 200 tasks; T1a evaluates 5 SLM families against them. The two papers mutually validate each other and can be submitted together as a combined NeurIPS ED Track paper if spring pre-work is feasible.
Sub-team Structure | [TBD — still deciding whether T1a and T1b are one team or two sub-teams. T1b is more systems/engineering-heavy; T1a is more ML/evaluation-heavy. Natural split if intern skills allow.]
Generation Strategies Compared | (A) Schema-Constrained Decoding: syntactic validity enforced at generation time, no execution. (B) Multi-Step Verification Pipeline: generate → mock-execute against schema simulator → filter. (C) Self-Play / Adversarial Multi-Agent: task generator vs. executor vs. verifier.
Dual Output Architecture | SFT Record: {instruction, tool_schema, verified_trace} — standard fine-tuning format. Eval Record: {instruction, intent_specification, ground_truth_trace, scope_constraints} — EnterpriseBench format. Same generation pass, two output modes.
Empirical Validation Domains | 3 public enterprise-adjacent API schemas: CRM (HubSpot public spec), Financial ops (Plaid-adjacent public spec), DevOps (GitHub Actions API). Fine-tune Qwen 2.5 7B + Llama 3 8B on each strategy's output. Measure: zero-shot → synthetic-SFT → real task performance gap.
GF Result | 12% tool-calling improvement from synthetic fine-tuning is CONFIDENTIAL. Reproduce fresh on public enterprise domains. Same hypothesis, new public data. This is the empirical validation the paper needs.
Intern Profile | Engineering-heavy: strong Python, REST APIs, JSON Schema, data pipelines. Less ML depth required than T1a. Good for a strong undergrad engineer or MS student with systems background.
Paper Lead | Spurthi Setty
Faculty Advisor | Prof. Yue Ning (Stevens CS — NLP) ¦ Prof. Wendy Hui Wang (Stevens CS — Trustworthy ML / Accountability)
Research Design Doc | [Paste Google Doc URL here]
Claude Code Prompt | [Paste Google Doc URL here]
GitHub Repo | [Paste GitHub URL — shared with T1a]
Venue / Conference | Type | Tier | Abstract Deadline | Full Paper Deadline | Conference Date | Template Format | Page Limit | Submission Status | CFP Link | Notes | Intern Lead | Last Updated
NeurIPS 2026 Evaluations & Datasets Track (combined T1a + T1b) | Full Conference — ED Track | Tier 1 ★ | May 4, 2026 (Pre-fellowship) | May 6, 2026 (Pre-fellowship) | Dec 6–12, 2026 | NeurIPS 1-col | 9 + refs | Requires Pre-work | https://neurips.cc/Conferences/2026/CallForEvaluationsDatasets | HIGHEST PRESTIGE. Submit T1a+T1b as ONE paper: framework (T1b) + benchmark built with it (T1a) + model results. ED Track explicitly welcomes benchmark construction methodology + dataset artifacts. Requires spring pre-work before fellowship. Code release mandatory at submission. | Spurthi (pre-fellowship) | [Date]
AAAI 2027 | Full Conference | Tier 1 ★ | Jul 25, 2026 | Aug 1, 2026 | Feb 16–23, 2027 | AAAI 2-col | 7 + refs | Not Started | https://aaai.org/conference/aaai/ | PRIMARY summer target for T1b standalone. Frame as methodology paper: how to generate enterprise agentic data from schema alone. Pairs naturally with T1a AAAI submission — two companion papers from same fellowship. | [Intern TBD] | [Date]
NeurIPS 2026 Workshops (Agentic AI / Synthetic Data) | Workshop | Tier 2 | ~Sep 2026 (TBC) | ~Sep–Oct 2026 (TBC) | Dec 6–12, 2026 | NeurIPS workshop 1-col | 4–8 | Not Started | https://neurips.cc/Conferences/2026 | Submit preliminary results (one API domain, 2 strategies) as 4-page workshop paper. Gets the framework in front of agentic AI community early. | [Intern TBD] | [Date]
ICLR 2027 | Full Conference | Tier 1 ★ | ~Oct 2026 (TBC) | ~Oct 2026 (TBC) | ~May 2027 | ICLR 1-col | 9 + refs | Not Started | https://iclr.cc | Stretch target. Strong fit if empirical validation shows clear gains across all 3 domains. Datasets & Benchmarks track or main track depending on framing. | [Intern TBD] | [Date]
Expert Systems with Applications (Elsevier Journal) | Journal | Tier 2 | Rolling | Rolling | ~3 months post-submission | Elsevier single-col | No limit | Not Started | https://www.sciencedirect.com/journal/expert-systems-with-applications | Post-fellowship journal extension combining T1a+T1b into one comprehensive paper. Same journal target as T4. Fast review cycle. | [Intern TBD] | [Date]
GENERATION STRATEGIES — ABLATION DESIGN
Strategy | Input Required | Execution Needed? | Syntactic Validity | Semantic Validity | Diversity | Compute Cost | Key Mechanism | Novelty
A — Schema-Constrained Decoding | API schema only | No | Enforced at generation | Schema-level only | Medium | Low | Constrained decoding (LMQL / Outlines) forces output to conform to JSON schema types, required fields, and enum values at token level. No execution simulator needed. | Partially — applying constrained decoding specifically to enterprise API schema generation with dual SFT+eval output is new.
B — Multi-Step Verification Pipeline | API schema + mock execution simulator | Mock only (no live API) | Enforced | Execution-logic validated | Medium-High | Medium | Generate candidate trace → build lightweight mock API from schema's type system + return value specs → simulate execution → filter traces where mock execution succeeds. Catches dependency errors (calling get_order before cancel_order) that schema constraints miss. | YES — mock execution from schema alone (no live API) is the core novel contribution. Prior work (APIGen) uses real executable APIs. This enables proprietary schema use.
C — Self-Play / Adversarial Multi-Agent | API schema only | No | Enforced | High — adversarial pressure | High | High | Task Generator model invents realistic enterprise instructions. Executor model generates tool-call traces. Verifier model critiques against intent specification. Adversarial loop: generator rewarded for tasks that challenge the executor. | YES — adversarial self-play for enterprise agentic data generation. Self-play exists in RL (AlphaGo) but not applied to tool-call trace generation from schema.
Baseline — Pure LLM Generation (no constraints) | API schema + few-shot examples | No | Not enforced | Not validated | Low | Very Low | Zero-shot or few-shot prompt GPT-4o with schema description. Generate instruction + trace directly. No verification. Included as lower bound — expect high hallucination rate. | No novelty — this is the naive baseline every practitioner would try first.
PRIOR WORK — HOW ENTERPRISESYNTH DIFFERS
Paper | Venue / Year | API Source | Multi-Step Traces | Schema-Only Input | Dual Output (SFT + Eval) | Intent Spec | Enterprise Focus
ToolLLM / ToolBench (Qin et al.) | ICLR 2024 | 16K public REST APIs (RapidAPI) | ✗ No | ✗ No | ✗ No | ✗ No | ✗ No
APIGen (Liu et al.) | NeurIPS 2024 D&B | 3,673 public executable APIs | ✗ No | ✗ No | ✗ No | ✗ No | ✗ No
APIGen-MT (Prabhakar et al.) | NeurIPS 2025 D&B | Public APIs + simulated user | ✓ Yes | ✗ No | ✗ No | ~ Partial | ✗ No
TOUCAN (Xu et al.) | arXiv Oct 2025 | 495 real-world MCP servers | ✓ Yes | ✗ No | ✗ No | ✗ No | ✗ No
EnterpriseSynth (THIS PAPER) | AAAI 2027 / NeurIPS 2026 ED | Any OpenAPI/Swagger spec — proprietary OK | ✓ Yes | ✓ Yes | ✓ Yes | ✓ Yes | ✓ Yes

## T2a — AnnotateBench
T2a: AnnotateBench — Benchmarking Annotation Requirements Across NLP Tasks
Research Question | How much labeled data do different annotation strategies need across NLP task types, and what do the learning curves look like?
Core Contribution | First systematic benchmark comparing annotation strategies (random, uncertainty AL, diversity AL, LLM-as-annotator, hybrid) across NLP task types with fitted learning curves and cost-accuracy Pareto frontiers
Key Finding (Hypothesis) | No single annotation strategy dominates across all task types; task complexity and pretraining coverage are the best predictors of annotation sufficiency
Experimental Design | 5 strategies × 10 datasets × 5 budget levels (10/50/100/500/1K labeled examples) × 3 model types = ~750 configurations. Shared codebase with T2b.
Task Types Covered | Text classification, NER, extractive QA, abstractive summarization, instruction tuning (5 task types, ≥2 datasets each)
Models | BERT-family fine-tuning (classification/NER), T5/FLAN-T5 (QA/summ), Llama 3 8B SFT (instruction tuning)
Sub-team A Lead Intern | [TBD — undergrad/MS capable of running systematic experiments]
Paper Lead | [TBD — senior intern or Spurthi]
Faculty Advisor | Prof. Yue Ning (Stevens CS — NLP) ¦ Prof. Wendy Hui Wang (Stevens CS — Trustworthy ML)
Shared with T2b | All experimental runs feed T2b ROI analysis. Same datasets, same models, different analytical lens.
Research Design Doc | [Paste Google Doc URL here]
Claude Code Prompt | [Paste Google Doc URL here]
GitHub Repo | [Paste GitHub URL here]
Venue / Conference | Type | Tier | Abstract Deadline | Full Paper Deadline | Conference Date | Template Format | Page Limit | Submission Status | CFP Link | Notes | Intern Lead | Last Updated
NeurIPS 2026 Evaluations & Datasets Track | Full Conference — ED Track | Tier 1 ★ | May 4, 2026 (Pre-fellowship) | May 6, 2026 (Pre-fellowship) | Dec 6–12, 2026 | NeurIPS 1-col | 9 + refs | Requires Pre-work | https://neurips.cc/Conferences/2026/CallForEvaluationsDatasets | HIGHEST PRESTIGE. Requires preliminary results by May 6 — before fellowship starts. Only viable with spring pre-work by Spurthi. ED Track explicitly welcomes annotation benchmarks and cost-accuracy analysis. Code release required at submission. | Spurthi (pre-fellowship) | [Date]
AAAI 2027 | Full Conference | Tier 1 ★ | Jul 25, 2026 | Aug 1, 2026 | Feb 16–23, 2027 | AAAI 2-col | 7 + refs | Not Started | https://aaai.org/conference/aaai/ | PRIMARY summer target. Submit the full benchmark paper. Frame as methodology: empirical scaling laws for annotation sufficiency across task types. Stronger play than DataPerf framing for AAAI audience. | [Intern TBD] | [Date]
NeurIPS 2026 Workshops (Data-centric AI / Human-in-the-Loop) | Workshop | Tier 2 | ~Sep 2026 (TBC) | ~Sep–Oct 2026 (TBC) | Dec 6–12, 2026 | NeurIPS workshop 1-col | 4–8 | Not Started | https://neurips.cc/Conferences/2026 | Parallel fast-track. Submit preliminary results (3 task types, 3 strategies) as 4-page workshop paper. Gets work in front of data-centric AI community before AAAI. | [Intern TBD] | [Date]
EMNLP 2026 Workshops | Workshop | Tier 2 | ~Aug 2026 (TBC) | ~Aug 2026 (TBC) | Oct 24–29, 2026 | ACL 2-col | 4–8 | Not Started | https://2026.emnlp.org | Good fit for NLP-focused annotation strategy comparison. Deadlines TBC — check Aug 2026. | [Intern TBD] | [Date]
Expert Systems with Applications (Elsevier Journal) | Journal | Tier 2 | Rolling | Rolling | ~3 months post-submission | Elsevier single-col | No limit | Not Started | https://www.sciencedirect.com/journal/expert-systems-with-applications | Post-fellowship journal extension. Combine T2a + T2b into a comprehensive annotation efficiency paper. Fast review cycle. | [Intern TBD] | [Date]
ANNOTATION STRATEGIES TO COMPARE
Strategy | Category | Query Selection Logic | Expected Strength | Expected Weakness | Implementation
Random Sampling | Baseline | Sample uniformly at random from unlabeled pool | Unbiased; establishes floor. Fast and reproducible. | Ignores model uncertainty; worst data efficiency in theory | Trivial — numpy.random.choice
Uncertainty Sampling (Least Confidence) | Active Learning | Query examples where model is least confident (max entropy or min margin) | Focused on decision boundary; most deployed in production | Suffers sampling bias with deep models; may query outliers | Hugging Face model + softmax entropy
Diversity Sampling (CoreSet / k-Center) | Active Learning | Select geometrically diverse subset in embedding space | Prevents mode collapse; good for class-imbalanced data | Computationally expensive at scale; ignores uncertainty | faiss k-means on sentence embeddings
BADGE (Batch Active learning by Diverse Gradient Embeddings) | Active Learning | Diverse + uncertain: k-means++ on gradient embeddings | Best of both worlds; state-of-the-art on multiple benchmarks | Requires gradient computation; slower than uncertainty sampling | Official BADGE repo (Ash et al. 2020)
LLM-as-Annotator (Zero-shot) | LLM Baseline | Use GPT-4o / Claude to label examples directly; no human | 30× cheaper than crowd-workers (Gilardi 2023); near-human on simple tasks | Unreliable on expert-domain tasks; anchoring bias risk; no calibration | Anthropic / OpenAI API + structured output
Human-LLM Hybrid (LLM label + human verify) | Hybrid — Anote's model | LLM labels all; human corrects only low-confidence or sampled examples | Best cost-accuracy tradeoff for most task types; Anote's core product | Anchoring bias when humans review LLM suggestions | Anote platform API + verifier model (Lapras-style)
DATASETS (10 TARGET DATASETS ACROSS 5 TASK TYPES)
Dataset | Task Type | Domain | Size (Total) | Classes / Output | Pretrain Coverage | HuggingFace ID | Notes
SST-2 | Text Classification | Sentiment | 67K | 2 | High | sst2 | Simple; establishes floor for classification
AGNews | Text Classification | News topics | 120K | 4 | High | ag_news | Well-studied; 4 classes
CoNLL-2003 | NER | News | 14K | 4 entity types | High | conll2003 | Standard NER benchmark
OntoNotes 5.0 | NER | Mixed | 76K | 18 entity types | Medium | ontonotes5 | Complex multi-class NER
SQuAD 2.0 | Extractive QA | Wikipedia | 130K | Span extraction | High | squad_v2 | Includes unanswerable questions
BioASQ | Extractive QA | Biomedical | ~16K | Span extraction | Low | bioasq | Low pretraining coverage — tests domain gap
XSum | Abstractive Summarization | News | 226K | Free text | High | xsum | Challenging abstractive task
SAMSum | Abstractive Summarization | Dialogue | 16K | Free text | Medium | samsum | Conversational domain
Alpaca-cleaned | Instruction Tuning | General | 52K | Free text | High | yahma/alpaca-cleaned | LLM fine-tuning baseline
FLAN collection subset | Instruction Tuning | Mixed | ~50K subset | Free text | High | Salesforce/dialogstudio | Diverse instruction types

## T2b — AnnotateROI
T2b: AnnotateROI — An Enterprise Framework for Measuring Annotation Return on Investment
Research Question | How should enterprises measure annotation ROI (F1-gain per labeling dollar) and determine when they have labeled enough data for production deployment?
Core Contribution | AnnotateROI: a standardized framework with (1) a formal ROI metric, (2) empirical cost-accuracy Pareto frontiers across strategies and tasks, (3) a practical stopping criterion, and (4) a decision tool for choosing between human, LLM, and hybrid annotation
Why This Gap Exists | No standardized academic metric for annotation ROI exists despite billions spent on labeling annually. Existing work (AWS ML Lens, industry guides) is informal and not empirically validated.
Key Deliverable | A decision framework enterprises can actually use: given task type, domain, current model performance, and labeling budget — which strategy maximizes ROI?
Builds On | T2a experimental results (all cost-accuracy data flows from T2a). T2b adds cost modeling, stopping criteria, and LLM-vs-human tradeoff analysis on top of T2a data.
Anote Platform Role | Provides real per-label cost data, annotation time logs, and quality scores from production labeling workflows — this is the key differentiator from academic benchmarks
Sub-team B Lead Intern | [TBD — prefer someone with interest in economics/decision theory or product analytics]
Paper Lead | [TBD — Natan or Spurthi]
Faculty Advisor | Prof. Yue Ning (Stevens CS) ¦ Prof. Jordan Suchow (Stevens Business — data science)
Research Design Doc | [Paste Google Doc URL here]
Claude Code Prompt | [Paste Google Doc URL here]
GitHub Repo | [Paste GitHub URL here]
Venue / Conference | Type | Tier | Abstract Deadline | Full Paper Deadline | Conference Date | Template Format | Page Limit | Submission Status | CFP Link | Notes | Intern Lead | Last Updated
AAAI 2027 | Full Conference | Tier 1 ★ | Jul 25, 2026 | Aug 1, 2026 | Feb 16–23, 2027 | AAAI 2-col | 7 + refs | Not Started | https://aaai.org/conference/aaai/ | PRIMARY TARGET. Frame as decision framework / tool paper. AAAI AI for Social Good or Human-Centered AI special track may also fit. Emphasize practical enterprise value and the novel ROI metric. | [Intern TBD] | [Date]
NeurIPS 2026 Evaluations & Datasets Track | Full Conference — ED Track | Tier 1 ★ | May 4, 2026 (Pre-fellowship) | May 6, 2026 (Pre-fellowship) | Dec 6–12, 2026 | NeurIPS 1-col | 9 + refs | Requires Pre-work | https://neurips.cc/Conferences/2026/CallForEvaluationsDatasets | Could submit combined T2a+T2b as one NeurIPS ED Track paper if spring pre-work is done. ED Track welcomes 'tools, analyses, or frameworks that improve how evaluative claims are constructed.' | Spurthi (pre-fellowship) | [Date]
NeurIPS 2026 Workshops (Data-centric AI / HITL) | Workshop | Tier 2 | ~Sep 2026 (TBC) | ~Sep–Oct 2026 (TBC) | Dec 6–12, 2026 | NeurIPS workshop 1-col | 4–8 | Not Started | https://neurips.cc/Conferences/2026 | Position paper on the ROI framework — present the metric and early results. Fast feedback from data-centric AI community. | [Intern TBD] | [Date]
Expert Systems with Applications (Elsevier Journal) | Journal | Tier 2 | Rolling | Rolling | ~3 months post-submission | Elsevier single-col | No limit | Not Started | https://www.sciencedirect.com/journal/expert-systems-with-applications | Combine T2a + T2b into a comprehensive journal paper post-fellowship. Elsevier fast track. Same journal target as T4. | [Intern TBD] | [Date]
ANNOTATEROI FRAMEWORK COMPONENTS
Component | Definition | Formula / Method | Data Source | Novel? | Notes
1. Annotation ROI Metric (aROI) | F1-point gain per annotation dollar spent, normalized by task difficulty | aROI = ΔF1 / ($cost_per_label × n_labels). Normalize by task ceiling (human expert F1). | T2a experiment results + Anote platform cost logs | YES — no standardized metric exists | Primary novel contribution. Allows direct cross-task, cross-strategy comparison.
2. Cost-Accuracy Pareto Frontier | For each task type: the Pareto-optimal annotation strategies at each budget level | Plot F1 vs. total annotation cost. Identify dominated strategies. Fit smooth frontier. | T2a experimental results (all 750 configs) | Partially — DataPerf has similar plots but not across task types or with LLM costs | Visualizes trade-off space. Key figure in the paper.
3. Learning Curve Extrapolation | Power-law fit to observed learning curve, used to predict performance at unseen budgets | F1(n) = F1_max - c·n^{-α}. Fit α and c from observed points. Predict saturation point. | T2a learning curve data | Application to annotation — novel. Extrapolation for stopping criterion. | Basis for stopping criterion. Task complexity features predict α.
4. Annotation Sufficiency Stopping Criterion | Decision rule: stop labeling when marginal gain drops below threshold θ | Stop when ΔF1/Δn < θ (user-specified threshold). Derive from fitted learning curve. | T2a learning curves + T2b cost model | YES — no published stopping criterion for HITL labeling pipelines | Practically the most valuable contribution. Enterprises need this directly.
5. LLM-vs-Human Decision Tree | Given task type, domain, budget, and accuracy target — which annotation mode is best? | Decision tree fitted on (task_type, domain_coverage, budget) → (recommended_strategy) | T2a cost-accuracy Pareto frontiers across all strategies | Partially — Gilardi 2023 compares for classification only | Generalizes Gilardi across 5 task types. Practical tool for enterprise teams.
6. Anchoring Bias Adjustment | Correction factor when humans review LLM suggestions — accounts for elevated false-positive rate | Adjust expected accuracy downward by empirically measured anchoring bias coefficient β | Human study on hybrid annotation (Lapras-style setup) — small n OK for pilot | YES — quantifying anchoring bias in production HITL is unstudied | Optional component depending on intern availability for human study.
KEY PAPERS TO CITE
Paper / Authors | Venue / Year | Key Contribution | Relevance to T2b
Settles, B. — Active Learning | Morgan & Claypool, 2012 | Definitive taxonomy of active learning strategies and query protocols | Foundation for strategy comparison and cost-reduction framing
Gilardi et al. — ChatGPT Outperforms Crowd-Workers | PNAS 2023 | ChatGPT exceeds crowd-worker accuracy at ~30× lower cost for classification | Motivates LLM-as-annotator baseline; covers only 1 task type
Zhou et al. — LIMA: Less Is More for Alignment | NeurIPS 2023 | 1K curated examples = 52K random for instruction tuning (Superficial Alignment Hypothesis) | Motivates data quality > quantity framing; key prior work for instruction tuning curve
Malladi et al. — LESS | ICML 2024 | 5% targeted data selection ≥ 100% for LLM fine-tuning | Upper bound on AL efficiency; shows selection matters enormously
Northcutt, Jiang, Chuang — Confident Learning | JAIR 2021 | Framework for identifying label errors; cleanlab package | Label quality dimension of ROI — errors reduce effective labeled set size
Ratner, Bach et al. — Snorkel / Data Programming | VLDB Journal 2020 | Programmatic labeling via labeling functions — 2.8× speedup | Weak supervision as low-cost strategy competing with active learning
Biegel et al. — Active WeaSuL | arXiv 2021 | Combining AL + weak supervision outperforms both when budgets ≤60 examples | Hybrid strategy baseline; especially relevant for Anote's product positioning
Hestness et al. — Deep Learning Scaling is Predictable | Baidu Research 2017 | Power-law learning curves across 4 domains; exponents −0.07 to −0.35 | Functional form for learning curve extrapolation component
DataPerf — Mazumder et al. | NeurIPS 2023 D&B | First benchmark suite for data-centric algorithms across multiple challenges | Most related prior benchmark — T2a+T2b extends to NLP + LLM + cost analysis
Schmarje et al. — Is One Annotation Enough? | NeurIPS 2022 D&B | Multiple annotations per example better approximate true label distributions | Motivates annotation quality dimension; supports multi-annotator designs

## T3 — Human-AI Teaming
T3: Human-AI Teaming for Preference Data & Red-Teaming
🚧 This track tab will be populated once research design is finalized. Duplicate the T1 tab structure and update accordingly.

## T4 — RAG Failure Prop.
T4: Failure Propagation in Agentic RAG Pipelines
🚧 This track tab will be populated once research design is finalized. Duplicate the T1 tab structure and update accordingly.

## T5 — RetrievalBench
T5: RetrievalBench — Cross-Domain Retrieval Technique Benchmark for Long Structured Documents
⟵ Feeds T4: RetrievalBench establishes baseline retrieval quality across domains. T4 takes the best-performing config from T5 and studies how residual retrieval errors propagate in multi-step agentic pipelines. T5 = input quality study; T4 = downstream consequence study.
📄 Extends arXiv:2404.07221 (Setty et al., 80+ citations): financial domain already benchmarked. This track adds 3 more domains (legal, medical, technical) with the same evaluation harness and introduces the full ablation design. Natural SIGIR 2027 full paper from the SIGIR 2026 short paper.
Research Question | Which combination of retrieval techniques (chunking, embedding fine-tuning, re-ranking, metadata annotation, query expansion) produces the best results for long structured documents — and does the winner generalize across domains?
Core Contribution | First controlled ablation benchmark comparing retrieval technique combinations across 4 structured document domains (financial, legal, medical, technical) with consistent evaluation metrics. Establishes cross-domain generalizability findings that practitioners can directly apply.
Why This Gap Exists | Every existing RAG improvement paper evaluates in one domain with one or two techniques. FinMTEB covers financial embeddings only; RAPTOR evaluates on general QA; domain embedding fine-tuning papers test in isolation. No paper has run a controlled ablation across multiple structured document domains simultaneously with consistent metrics.
RQ1 — Marginal Contribution | Which single technique contributes the most marginal improvement across all domains? Hypothesis: cross-encoder re-ranking and LLM-generated metadata annotation are the highest-value additions.
RQ2 — Cross-Domain Generalizability | Does the winning full-pipeline configuration on financial documents also win on legal, medical, and technical? If not, what predicts which technique works in which domain?
RQ3 — Document Structure × Technique Interaction | Hypothesis: metadata annotation helps more for heterogeneous-structure documents (10-Ks with tables/sections) and less for more uniform documents (clinical notes). Structure complexity predicts annotation value.
Datasets | Financial: FinanceBench (150 public rows — arXiv baseline already done). Legal: CUAD (500 contracts, 41 question types). Medical: PubMedQA + MedQA subset. Technical: TechQA (IBM) or DocFinQA technical subset.
Technique Configs (6 ablation levels) | Baseline (fixed-size chunks, generic BGE, no reranking, no metadata, no QE) → +Semantic Chunking → +Domain Fine-tuned Embedding → +Cross-encoder Reranking → +LLM Metadata Annotation → +HyDE Query Expansion (Full pipeline). 6 configs × 4 domains = 24 experimental conditions.
Evaluation Metrics | Retrieval: Page-level accuracy, NDCG@10. Answer: GPT-4o LLM-eval score, RAGAS faithfulness + context relevance. Efficiency: Latency per query, cost per query (key for practitioner applicability).
Head Start | Financial domain results from arXiv:2404.07221 provide Baseline and +QE configs already. Only need to run +Chunking, +Embedding, +Reranking, +Metadata configs for financial and all 6 configs for legal/medical/technical. Saves ~30% of experimental compute.
Intern Profile | Moderate ML + strong engineering. Needs Python, LangChain/LlamaIndex familiarity, vector DB experience. Good for a strong undergrad with RAG project experience or MS student. One intern can handle financial/legal; second intern handles medical/technical.
Paper Lead | Spurthi Setty (first author — extends her arXiv paper)
Faculty Advisor | Prof. Yue Ning (Stevens CS — NLP, information retrieval) ¦ External: cite existing reviewers from SIGIR 2026 submission as context
Research Design Doc | [Paste Google Doc URL here]
Claude Code Prompt | [Paste Google Doc URL here]
GitHub Repo | [Paste GitHub URL here — can share eval harness with T4]
Venue / Conference | Type | Tier | Abstract Deadline | Full Paper Deadline | Conference Date | Template Format | Page Limit | Submission Status | CFP Link | Notes | Intern Lead | Last Updated
SIGIR 2027 | Full Conference | Tier 1 ★ | ~Jan 2027 (TBC) | ~Jan 2027 (TBC) | ~Jul 2027 | ACM 2-col | 9 + refs | Not Started | https://sigir.org | PRIMARY TARGET — natural home for this paper. SIGIR published the arXiv paper's SIGIR 2026 short paper submission. Full paper extending to 4 domains + full ablation is the canonical SIGIR paper. Deadline TBC — historically January for July conference. | [Intern TBD] | [Date]
AAAI 2027 | Full Conference | Tier 1 ★ | Jul 25, 2026 | Aug 1, 2026 | Feb 16–23, 2027 | AAAI 2-col | 7 + refs | Not Started | https://aaai.org/conference/aaai/ | BACKUP if SIGIR timing doesn't work. Frame as cross-domain RAG benchmark. AAAI covers information retrieval and NLP. Strong fit. Same August 1 deadline as all other tracks. | [Intern TBD] | [Date]
NeurIPS 2026 Evaluations & Datasets Track | Full Conference — ED Track | Tier 1 ★ | May 4, 2026 (Pre-fellowship) | May 6, 2026 (Pre-fellowship) | Dec 6–12, 2026 | NeurIPS 1-col | 9 + refs | Requires Pre-work | https://neurips.cc/Conferences/2026/CallForEvaluationsDatasets | Only viable if Spurthi can run the 3 new domains before fellowship starts. Financial already done. Legal + medical could be pre-computed. ED Track is ideal venue for a benchmark paper. Code release required. | Spurthi (pre-fellowship) | [Date]
ACL 2026 Workshop RAG4Report | Workshop | Tier 2 | Mar 6, 2026 (PASSED) | Mar 6, 2026 (PASSED) | ~Aug 2026 | ACL 2-col | 4–8 | Missed | https://openreview.net/group?id=aclweb.org/ACL/2026/Workshop/RAG4Report | RAG4Report workshop — directly relevant. Missed this cycle. Flag for ACL 2027 workshop equivalent. | N/A | [Date]
Expert Systems with Applications (Elsevier Journal) | Journal | Tier 2 | Rolling | Rolling | ~3 months post-submission | Elsevier single-col | No limit | Not Started | https://www.sciencedirect.com/journal/expert-systems-with-applications | JOURNAL EXTENSION of arXiv:2404.07221. Combine original financial results + 3 new domains into one comprehensive journal paper. Same target as T4. Fast Elsevier review cycle. This is the clearest journal path given existing citation base. | [Intern TBD] | [Date]
CIKM 2026 | Full Conference | Tier 2 | ~May 2026 (TBC) | ~May 2026 (TBC) | ~Oct 2026 | ACM 2-col | 9 + refs | Not Started | https://www.acm.org/conferences/cikm | CIKM covers information retrieval, knowledge management, data mining. Good fit for retrieval benchmark. Verify 2026 deadline — may align with fellowship. | [Intern TBD] | [Date]
ABLATION DESIGN — 6 PIPELINE CONFIGURATIONS × 4 DOMAINS = 24 CONDITIONS
Config | Chunking | Embedding | Re-ranking | Metadata Annotation | Query Expansion | Financial (Baseline) | Legal (New) | Medical (New) | Technical (New) | Est. Compute
C0 — Baseline | Fixed-size 512 tokens | Generic BGE (no fine-tune) | None | None | None | ✓ Done | Run | Run | Run | Low — fast
C1 — +Semantic Chunking | Element-based (RAPTOR/Unstructured) | Generic BGE | None | None | None | ~ Partial | Run | Run | Run | Low
C2 — +Domain Embedding | Element-based | Domain fine-tuned (contrastive, 5K pairs) | None | None | None | ~ Partial | Run | Run | Run | Med — fine-tune cost
C3 — +Cross-encoder Reranking | Element-based | Domain fine-tuned | BGE-reranker-large (cross-encoder) | None | None | ~ Partial | Run | Run | Run | Med
C4 — +LLM Metadata | Element-based | Domain fine-tuned | Cross-encoder | GPT-4o mini generates keywords + doc type + summary | None | ✓ Done | Run | Run | Run | Med-High — LLM cost
C5 — Full Pipeline (+HyDE QE) | Element-based | Domain fine-tuned | Cross-encoder | LLM-generated metadata | HyDE: generate hypothetical doc, embed, retrieve | ✓ Done | Run | Run | Run | High — all components
DOMAIN × DATASET REFERENCE
Domain | Dataset | Size | Doc Type | Terminology Density | Structural Complexity | Public? | HuggingFace / Source | Status | Notes
Financial | FinanceBench (Patronus AI) | 150 public rows (full: 10,231) | 10-K, 10-Q, 8-K, Earnings | High — financial terms | High — tables, sections, footnotes | Yes (150 rows) | patronusai/financebench | DONE — baseline results in arXiv:2404.07221 | Ground truth answers + evidence strings + page numbers. Ideal eval format.
Legal | CUAD — Contract Understanding Atticus Dataset | 500 contracts 41 question types | Commercial contracts | High — legal jargon | High — sections, definitions, cross-refs | Yes | theatticusproject/cuad | TODO — no existing results | Expert-annotated clause extraction. 13K+ labeled clauses. Perfect structured doc benchmark.
Medical/Clinical | PubMedQA + MedQA subset | ~1K eval questions | Biomedical literature + clinical QA | Very high — clinical abbrevs | Medium — structured abstracts | Yes | qiaojin/PubMedQA GBaker/MedQA-USMLE | TODO — no existing results | Mix of literature-style + clinical-style. Tests two subdomains of medical retrieval.
Technical/Manufacturing | TechQA (IBM) or DocFinQA technical subset | ~1.4K eval questions | Technical manuals, spec sheets | High — product/engineering terms | Medium — numbered sections | Yes | ibm/techqa | TODO — no existing results | IBM technical support document QA. Closest analogue to GF manufacturing context.

## T-Theory — Low Priority
T-Theory: Sample Complexity Theory for Active Learning — DEPRIORITIZED
⚠️ This track is DEPRIORITIZED. Activate only if a theory-capable intern is recruited (top MS / PhD-track with PAC learning background). See research design doc for scope.
Why deprioritized | Proving novel sample complexity bounds beyond the NTK regime requires years of specialist expertise in functional analysis and concentration inequalities. A 'developing' theory background is not sufficient for first-author novel theory work.
What IS tractable (if activated) | A hybrid paper: (1) empirically test whether NTK-based active learning predictions match practical deep AL behavior, (2) show learning curves in the double-descent regime, (3) cite Hanneke 2025 (agnostic AL always better than passive) as theoretical motivation for the empirical study.
Activation criteria | Recruit an intern with: (a) coursework in statistical learning theory (PAC learning, Rademacher complexity), (b) comfort reading Hanneke / Balcan papers, (c) explicit interest in theoretical ML. If this intern exists, activate this track. Otherwise, keep deprioritized.
Best hook if activated | Hanneke (NeurIPS 2025, Oral) proved agnostic AL is always strictly better than passive learning. This resolves a 20-year open problem. A paper empirically validating this result in the deep learning / LLM fine-tuning setting — connecting the theory to practice — is a natural and publishable contribution.
Key papers to read first | Hanneke (JMLR 2014 survey); Balcan, Hanneke, Vaughan (ML 2010); Bartlett, Harvey, Liaw, Mehrabian (JMLR 2019 — VC dimension); Hanneke (NeurIPS 2025 — agnostic AL); Wang et al. (NeurIPS 2021 — only neural net active learning theory paper).
Venue if activated | COLT 2027 (June deadline ~Jan 2027), NeurIPS 2027, ICML 2027, or ALT (Algorithmic Learning Theory). Not AAAI — wrong audience for pure theory.

## ℹ️ How to Use
HOW TO USE THIS TRACKER
SETUP (Do Once)
1. Upload this file to Google Sheets: File → Import → Upload
2. Create a Google Drive folder: 'Anote Fellowship 2026'
3. Create one subfolder per track: T1-AgenticEval, T2-ActiveLearning, T3-HumanAI, T4-RAGPipeline
4. In each subfolder, create: Research Design Doc, Claude Code Prompt Doc, LaTeX Template
5. Paste the Google Doc URLs into the [Placeholder] cells in Master Overview and each track tab
6. Share the sheet with Natan, Spurthi, and interns (Editor access)
WEEKLY MAINTENANCE
• Update 'Submission Status' column as work progresses (Not Started → In Progress → Submitted → Accepted/Rejected)
• Update 'Last Updated' column when you edit a row
• Check TBC deadline rows in Aug–Oct 2026 — NeurIPS and EMNLP workshop deadlines will be announced then
• Add new venues as they are announced by adding rows to the relevant track tab
STATUS DEFINITIONS
Not Started — No work begun on this submission
In Progress — Benchmark/experiments running, paper being drafted
Submitted — Paper submitted to venue, awaiting decision
Accepted — Paper accepted 🎉
Rejected — Paper rejected; note lessons learned in Notes column
ADDING NEW TRACKS
• Duplicate the 'T1 — Agentic Eval' tab
• Update the banner, metadata block, hypotheses, and venue rows
• Add a row in the Master Overview tab
• Create a corresponding subfolder in Google Drive
LATEX TEMPLATE FORMATS BY VENUE
AAAI 2027 → AAAI 2-column format (aaai26.sty — use latest year)
NeurIPS 2026 workshops → NeurIPS workshop 1-col (neurips_2024.sty or similar)
EMNLP 2026 workshops → ACL 2-column (acl_latex.sty)
ICLR 2027 → ICLR 1-column (iclr2024_conference.sty)
EUMAS 2026 → Springer LNCS (llncs2e.sty)
Expert Systems with Applications → Elsevier single-column (elsarticle.cls)
→ All templates are linked in the track tabs. The anote_paper_template.tex file covers all venues.